## Development Timeline
Phase | Case | Task | Deliverables | Technical Focus | Files Created/Enhanced | Status | Date Range
Phase 1: Foundation & Authentication System | Case 1: User Authentication Infrastructure | Implement secure user registration and login system | registration.php with form validation and password, login.php with session management, includes/config.php with security constants and database setup, Basic CSS styling for authentication forms | PHP sessions, input sanitization, form validation | pages/register.php, pages/login.php, includes/config.php | Complete | July 3-5
Phase 1: Foundation & Authentication System | Case 2: Homepage Dashboard Design | Create detective-themed dashboard with user statistics | index.php with personalized dashboard, Case progress tracking display, Quick action navigation buttons, Terminal-style CSS theme implementation | CSS Grid layouts, terminal aesthetics, responsive design | index.php, assets/css/main.css, assets/css/page_specific_css/page_home.css | Complete | July 3-5
Phase 2: Case Management System | Case 3: Case Browser Implementation | Build interactive case selection interface | cases.php with filtering and categorization, Case difficulty badge system, Case status tracking (new, in-progress, completed), Responsive case grid layout | CSS Grid with auto-fill, hover animations, filtering logic | pages/cases.php, assets/css/page_specific_css/page_cases.css | Complete | July 6-7
Phase 2: Case Management System | Case 4: Investigation Interface Foundation | Create main investigation workspace | investigate.php with evidence collection system, Split-screen layout (65% main, 35% sidebar), Evidence hotspot interaction system, Basic hint system implementation | Complex CSS layouts, JavaScript-free interactions, session state management | pages/investigate.php, assets/css/page_specific_css/page_investigate.css | Complete | July 6-7
Phase 3: Advanced Investigation Features | Case 5: Evidence Cross-Reference System | Implement visual evidence connection analysis | analyze_evidence.php with draggable evidence nodes, Cross-reference visualization with connection lines, Evidence correlation scoring algorithm, Interactive evidence board with coordinate tracking | CSS transforms, position absolute, PHP coordinate tracking | pages/analyze_evidence.php, assets/css/page_specific_css/page_analyze_evidence.css | Complete | July 8-9
Phase 3: Advanced Investigation Features | Case 6: Solution Submission Engine | Build case completion and scoring system | submit_solution.php with suspect selection interface, Complex scoring algorithm with multiple factors, Solution validation against correct answers, Real-time score preview system | Multi-factor algorithms, mathematical calculations, data validation | pages/submit_solution.php, assets/css/page_specific_css/page_submit_solution.css | Complete | July 8-9
Phase 4: Results & Community Features | Case 7: Performance Analysis Dashboard | Create detailed results and analytics system | results.php with comprehensive score breakdown, Performance rating system with visual indicators, Achievement tracking and badge system, Comparison with optimal solutions | Data visualization, progress bars, conditional styling | pages/results.php, assets/css/page_specific_css/page_results.css | Complete | July 10-11
Phase 4: Results & Community Features | Case 8: Community Leaderboard System | Implement competitive ranking and social features | leaderboard.php with multiple sorting criteria, User profile system with statistics and achievements, Community performance comparison, Hall of fame highlighting system | Array sorting algorithms, JSON data aggregation, community statistics | pages/leaderboard.php, pages/profile.php, assets/css/page_specific_css/page_leaderboard.css, assets/css/page_specific_css/page_profile.css | Complete | July 10-11
Phase 4: Integration & Polish | Case 9: Data Persistence & Progress System | Implement comprehensive progress saving and restoration | includes/cases.php with all case definitions and logic, includes/json_helpers.php with data management functions, Progress auto-save functionality across all investigation phases, JSON-based storage system with atomic operations | File I/O operations, race condition prevention, data integrity | includes/cases.php, includes/json_helpers.php | Complete | July 12
Phase 4: Integration & Polish | Case 10: Mobile Optimization & Responsive Design | Ensure cross-device compatibility and performance optimization | Mobile-responsive navigation with CSS-only hamburger menu, Responsive breakpoints for all page layouts, Touch-friendly interface elements, Performance optimization and CSS animation refinement | CSS media queries, transform animations, mobile UX | assets/css/style.css, includes/navbar.php | Complete | July 12